## Gantt Chart
GANTT CHART
PROJECT TITLE |  | Pengembangan Otomasi Perpustakaan |  |  |  |  | COMPANY NAME | [6 empty] | UPT PERPUSTAKAAN PROVINSI DINAS KEARSIPAN DAN PERPUSTAKAAN PROVINSI JAWA TENGAH
PROJECT MANAGER |  | Sageri Fikri Ramadhan |  |  |  |  | DATE | [6 empty] | 31/10/2019
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Evaluasi Kasus Terkait dan Rekomendasi Rancangan Project | Aji P. | 2019-10-31 | 2019-11-01 | 1 | 100% | bar: WEEK 1 R
1.2 | Penyusunan Project Charter | Sageri F. | 2019-10-31 | 2019-11-01 | 1 | 100% | bar: WEEK 1 R
1.2.1 | Definisikan Project System | Riyan K. | 2019-10-31 | 2019-11-01 | 1 | 0%
1.2.2 | Resource Plan | Riyan K. | 2019-10-31 | 2019-11-01 | 1 | 0%
1.2.3 | Implementation Plan | Aji P. | 2019-10-31 | 2019-11-01 | 1 | 0%
1.2.4 | Project Plan | Yulistia E. | 2019-10-31 | 2019-11-01 | 1 | 0%
1.2.5 | WBS | Yulistia E. | 2019-10-31 | 2019-11-01 | 1 | 100% | bar: WEEK 1 R
1.3 | Presentasi Project Charter kepada PM | Sageri F. | 2019-11-01 | 2019-11-02 | 1 | 0%
1.4 | Penyesuaian kembali Project Charter (Bilamana diperlukan) | Sageri F. | 2019-11-01 | 2019-11-02 | 1 | 0%
1.5 | Project Charter : Approved | Sageri F. | 2019-11-04 | 2019-11-04 | 0 | 0%
2 | Project Definition and Planning
2.1 | Preliminary Scope Statement | Sageri F. | 2019-11-05 | 2019-11-06 | 1 | 0%
2.1.1 | Identifikasi Scope | Riyan K. | 2019-11-05 | 2019-11-06 | 1 | 0%
2.2 | Definisi Project Team | Aji P. | 2019-11-05 | 2019-11-06 | 1 | 0%
2.3 | First Meet and Brainstroming 1 | Sageri F. | 2019-11-06 | 2019-11-07 | 1 | 0%
2.4 | Perencanaan Schedule Management Plan | Yulistia E. | 2019-11-06 | 2019-11-07 | 1 | 0%
2.5 | Pembuatan SRS | Yulistia E. | 2019-11-06 | 2019-11-08 | 2 | 0%
2.5.1 | User Requirement Gathering | Aji P. | 2019-11-06 | 2019-11-08 | 2 | 0%
2.6 | Pembuatan SDD | Yulistia E. | 2019-11-08 | 2019-11-10 | 2 | 0%
2.6.1 | Perancangan Design System | Riyan K. | 2019-11-08 | 2019-11-11 | 3 | 0%
2.7 | Perancangan Cost Management Plan | Yulistia E. | 2019-11-11 | 2019-11-12 | 1 | 0%
2.7.1 | Identifikasi Kebutuhan Installasi | Aji P. | 2019-11-11 | 2019-11-12 | 1 | 0%
3 | Project Conception and Initiation
3.1 | Pengadaan Kebutuhan Perangkat Keras | Riyan K. | 2019-11-11 | 2019-11-13 | 2 | 0%
3.2 | Installasi Awal Perangkat Keras | Aji P. | 2019-11-12 | 2019-11-15 | 3 | 0%
3.2.1 | Pemasangan RFID Tags pada setiap buku | Riyan K. | 2019-11-13 | 2019-11-16 | 3 | 0%
3.2.2 | Pemasangan sensor RFID pada Tiap Gate di Area Sirkulasi | Yulistia E. | 2019-11-12 | 2019-11-15 | 3 | 0%
3.2.3 | Pemasangan Self-Loan Computer pada Area Sirkulasi | Aji P. | 2019-11-15 | 2019-11-18 | 3 | 0%
3.2.4 | Penyiapan Jaringan Intranet untuk setiap perangkat keras | Aji P. | 2019-11-18 | 2019-11-18 | 0 | 0%
3.2.4.1 | Penyiapan Server | Riyan K. | 2019-11-16 | 2019-11-16 | 0 | 0%
3.2.4.2 | Installasi Cable Management | Riyan K. | 2019-11-18 | 2019-11-18 | 0 | 0%
3.3 | Installasi Perangkat Lunak | Yulistia E. | 2019-11-15 | 2019-11-17 | 2 | 0%
3.3.1 | Pembuatan Aplikasi Web/Sistem Informasi Ndalem Perpus | Aji P. | 2019-11-18 | 2019-11-21 | 3 | 0%
3.4 | Integration Session | Sageri F. | 2019-11-21 | 2019-11-23 | 2 | 0%
3.5 | Merampungkan Dokumen Project | Yulistia E. | 2019-11-20 | 2019-11-24 | 4 | 0%
3.6 | Deployment System | Sageri F. | 2019-11-22 | 2019-11-24 | 2 | 0%
4 | Project Performance / Monitoring
4.1 | Pengujian Program | Sageri F. | 2019-11-24 | 2019-11-26 | 2 | 0%
4.2 | Revisi Sistem (Bila Ada) | Aji P. | 2019-11-24 | 2019-11-26 | 2 | 0%
4.3 | Risk Management Document | Yulistia E. | 2019-11-24 | 2019-11-26 | 2 | 0%
4.4 | Membuat User Guide dan Error Handling Document | Riyan K. | 2019-11-24 | 2019-11-29 | 5 | 0%
5 | Project Performance / Monitoring
5.1 | Rilis Program | Sageri F. | 2019-11-29 | 2019-11-30 | 1 | 0%