## Struktur Organisasi
Ndalem Perpus Company Organizational Chart
[42]
System Engineering
Aji Priambodo Santoso
Independent Test Group
Riyan Kuncoro Jati
Project Manager
Sageri Fikri Ramadhan
Project Technical Lead
Yulistia Elsa Nursida
S/W Subproject Manager 1
Rahma
S/W Subproject Manager 2
Aditya Hardiansyah
H/W Subproject Manager
Rakha
Quality Assurance
Sarah Aulia
Configuration Management
Muhammad Daffa
Team 1
Team 2
Team 3
Team 1
Team 2
Team 3
Team 1
Team 2

## RAMRACI
|  | Design & System Engineering | Hardware Develoment | Software Development | Unit Testing Dept | Quality Assurance | Training
1 | Project Conception and Initiation
1.1 | Evaluasi Kasus Terkait dan Rekomendasi Rancangan Project | R | A | A | C | C | I
1.2 | Penyusunan Project Charter | R | A | A | A | C | I
1.2.1 | Definisikan Project System | R | A | A | C | I | I
1.2.2 | Resource Plan | R | A | C | C | I | I
1.2.3 | Implementation Plan | A | R | C | C | I | I
1.2.4 | Project Plan | A | R | C | I | I | I
1.2.5 | WBS | A | R | C | I | I | I
1.3 | Presentasi Project Charter kepada PM | R | A | C | C | I | I
1.4 | Penyesuaian kembali Project Charter (Bilamana diperlukan) | R | C | C | C | I | I
1.5 | Project Charter : Approved | I | I | I | I | I | I
2 | Project Definition and Planning
2.1 | Preliminary Scope Statement | R | C | C | A | I | I
2.1.1 | Identifikasi Scope | R | C | C | I | A | I
2.2 | Definisi Project Team | R | C | C | A | I | I
2.3 | First Meet and Brainstroming 1 | R | C | C | I | A | I
2.4 | Perencanaan Schedule Management Plan | A | C | C | A | I | I
2.5 | Pembuatan SRS | R | C | A | I | I | I
2.5.1 | User Requirement Gathering | R | C | A | I | I | I
2.6 | Pembuatan SDD | R | C | A | I | I | I
2.6.1 | Perancangan Design System | R | C | A | I | I | I
2.7 | Perancangan Cost Management Plan | R | C | A | I | I | I
2.7.1 | Identifikasi Kebutuhan Installasi | R | A | C | C | I | I
3 | Project Conception and Initiation
3.1 | Pengadaan Kebutuhan Perangkat Keras | C | R | IA | I/A | I/A | I/A
3.2 | Installasi Awal Perangkat Keras | C | R | A | I/A | I/A | I/A
3.2.1 | Pemasangan RFID Tags pada setiap buku | C | R | A | I/A | I/A | I/A
3.2.2 | Pemasangan sensor RFID pada Tiap Gate di Area Sirkulasi | C | R | A | I/A | I/A | I/A
3.2.3 | Pemasangan Self-Loan Computer pada Area Sirkulasi | C | R | A | I/A | I/A | I/A
3.2.4 | Penyiapan Jaringan Intranet untuk setiap perangkat keras | C | R | A | I/A | I/A | I/A
3.2.4.1 | Penyiapan Server | C | R | A | I/A | I/A | I/A
3.2.4.2 | Installasi Cable Management | C | R | A | I/A | I/A | I/A
3.3 | Installasi Perangkat Lunak | C | A | R | I/A | I/A | I/A
3.3.1 | Pembuatan Aplikasi Web/Sistem Informasi Ndalem Perpus | C | A | R | I/A | I/A | I/A
3.4 | Integration Session | C | A | R | I/A | I/A | I/A
3.5 | Merampungkan Dokumen Project | C | A | R | I/A | I/A | I/A
3.6 | Deployment System | C | A | R | I/A | I/A | I/A
4 | Project Performance / Monitoring
4.1 | Pengujian Program | I | R/I | R/I | R | R | I
4.2 | Revisi Sistem (Bila Ada) | I | R/I | R/I | R | R | I
4.3 | Risk Management Document | I | R/I | R/I | R | R | I
4.4 | Membuat User Guide dan Error Handling Document | I | R/I | R/I | R | R | I
5 | Project Performance / Monitoring
5.1 | Rilis Program | I | C | C | A | I | R